SLAB WORTHY™

1.0 Launch Roadmap

San Diego Comic-Con • July 23, 2026

5 months to launch • Physical booth + Digital launch

| Beta Launch April 2026 | SDCC Launch July 23, 2026 |
| --- | --- |

Prepared: February 23, 2026

# Where We Are Today

Slab Worthy has a working product with real infrastructure. The core grading engine, Slab Guard anti-theft system, sales data pipeline, and billing are all functional. This roadmap is about going from working to launch-ready.

What’s Built & Working

| System | Status |
| --- | --- |
| AI Grading Engine | 4-photo Claude Vision analysis, FMV lookup, slab-or-skip verdict |
| Sales Database | 50,000+ sales from eBay & Whatnot, daily growth via extensions |
| Slab Guard Registry | Comic registration, fingerprinting, serial tracking |
| Slab Guard Verify | Public verification page with Turnstile, photo matching |
| Sighting System | Report to Owner flow, owner dashboard alerts, response actions |
| Chrome Extension (eBay) | Slab Guard monitor, eBay sales capture, bid filter |
| Chrome Extension (Whatnot) | Live auction valuator, Vision scanning, auto-scan, sale tracking |
| Backend API | Flask on Render (Docker), 14 route blueprints, JWT auth, CORS |
| Frontend | Cloudflare Pages, PWA, universal footer, 17 HTML pages |
| Billing | Stripe integration, 4 tiers (Free/Pro/Guard/Dealer), plan gating |
| Contact Form | Resend email, Turnstile spam protection, topic routing |
| Vision API Proxy | Server-side Anthropic calls, daily scan caps, usage logging |

# Must-Haves for 1.0

These are launch blockers. Without these, we don’t launch.

1. Grading Consistency

The core product. Right now the AI can return different grades for identical photos. For a paid product—especially one people will try live at a booth—this must be reliable and repeatable.

- Implement grading calibration layer (normalize Claude’s output against known graded comics)

- Build a test suite of 50+ comics with known CGC grades for regression testing

- Target: same photos should produce grades within ±0.5 points, 95% of the time

- Add confidence scoring (“High confidence: 9.2” vs “Low confidence: 7–8 range”)

2. Mobile Experience

At SDCC, everyone is on their phone. The grading flow must work flawlessly on mobile—camera capture, photo upload, results display.

- Full mobile audit of grading flow (camera → upload → results)

- Direct camera capture (not file picker) for each of the 4 angles

- Responsive design pass on all public pages (index, pricing, about, FAQ, contact)

- Touch-optimized UI (larger tap targets, swipe gestures for results)

3. Onboarding & First-Time Experience

At the booth, someone picks up their phone and needs to go from zero to graded comic in under 2 minutes. No friction.

- Streamlined sign-up (email + password, skip email verification for first grade)

- Guided first-grade walkthrough (“Step 1: Take a photo of the front cover”)

- Free tier gets 2 grades (enough to try at the booth, not enough to never pay)

- QR code → landing page → sign up → grade (single funnel, no dead ends)

4. Photo Quality Gate

Users will submit blurry, dark, cropped photos. The AI can’t grade what it can’t see. We need client-side checks before the photo even leaves the phone.

- Blur detection (reject photos below sharpness threshold)

- Brightness check (too dark / too washed out)

- Minimum resolution check

- Real-time feedback with fix instructions (“Too dark — try near a window”)

5. Results & Grading Report

The grading result is the money moment. It needs to feel authoritative and be immediately useful.

- Single-screen slab report: grade, confidence, FMV at that grade, slab-or-skip verdict

- Breakdown of defects found (spine ticks, color breaks, corner wear) with photo annotations

- Shareable result card (image users can save/post to social media)

- Grade history in account page (re-grade comparison over time)

6. Billing & Payment Polish

People need to be able to sign up, pay, and start using premium features without hitting any dead ends.

- End-to-end Stripe Checkout tested for all tiers

- Plan upgrade/downgrade flow

- Usage limits enforced and clearly communicated (“3 of 10 grades used this month”)

- Cancellation flow (self-serve, no support ticket needed)

7. Infrastructure & Reliability

A booth demo that crashes is worse than no demo. The backend needs to handle a surge of sign-ups.

- Load testing: simulate 100 concurrent grading requests

- Render plan upgrade if needed (current plan may not handle burst traffic)

- Error handling pass: no raw stack traces, friendly messages everywhere

- Monitoring & alerting (uptime checks, error rate alerts)

- Database backups verified and restorable

8. Analytics & Tracking

We need to know what’s happening from day one: who’s signing up, who’s grading, who’s paying.

- Google Analytics or Plausible on all pages

- Conversion funnel tracking (visit → sign-up → first grade → paid)

- Admin dashboard: daily sign-ups, grades, revenue

# Nice-to-Haves

Would make the launch stronger but won’t block it. Prioritize after must-haves are locked.

Email System

- Welcome email after sign-up (already have Resend—just need templates)

- Grading result email (“Your comic graded at 8.5 — here’s your report”)

- Sighting alert emails (owner notified when their comic is spotted)

SMS / Text Alerts (Twilio)

- Opt-in text alerts for Slab Guard sightings

- Premium feature for Guard/Dealer tiers

Landing Page Optimization

- Hero section with animated demo or video

- Social proof (testimonials from beta testers, grade accuracy stats)

- SEO optimization (meta tags, Open Graph, structured data)

- SDCC-specific landing page (/sdcc) with show-exclusive offer

Demo / Try-Before-You-Buy Mode

- Sample grading with a pre-loaded comic (no sign-up needed to see what results look like)

- Great for booth traffic—“scan this comic” demo station

Collection Gallery Improvements

- Grid/list view toggle, cover thumbnails

- Total collection value estimate

- Export to CSV/PDF

Chrome Web Store Publishing

- Slab Guard Monitor extension published and installable

- Whatnot Valuator extension published (or invite-only for Dealer tier)

# Stretch Goals

Only if everything else is done early. These are post-launch features that would be great to tease at SDCC.

Native Mobile App

PWA wrapper or React Native app. “Download Slab Worthy” is a stronger pitch than “go to our website.” Could be App Store / Google Play listing even if it’s just a thin wrapper.

AI Comic Identification

Point your camera at any comic and identify it—title, issue, variant, key status—without typing anything. The Whatnot extension already does this via Vision; bringing it to the main app would be huge.

Dealer Dashboard & Bulk Grading

Upload a stack of 20 comics, get grades for all of them. Dealer-tier feature. CSV export with grades, FMVs, and slab recommendations for the whole batch.

API for Third Parties

Public API for comic shops, auction houses, or other apps to integrate Slab Worthy grading. Paid per-call or bundled with Dealer tier.

Grading Certificate PDF

Downloadable PDF report with the Slab Worthy grade, defect analysis, FMV data, and a QR code linking to the verification page. Not a replacement for CGC/CBCS, but useful for raw sales.

# Timeline

Five phases from now to SDCC. Each phase has a clear milestone that must be hit before moving on.

| Dates | Milestone | Status |
| --- | --- | --- |
|  | PHASE 1: CORE HARDENING |  |
| Feb 24 – Mar 14 | Grading consistency: calibration layer + 50-comic test suite | Not Started |
| Mar 1 – Mar 21 | Mobile experience: full grading flow on iOS Safari & Android Chrome | Not Started |
| Mar 7 – Mar 28 | Photo quality gate: blur, brightness, resolution checks | Not Started |
| Mar 14 – Mar 31 | Grading report redesign: single-screen, shareable, defect breakdown | Not Started |
|  | PHASE 2: BETA LAUNCH |  |
| Apr 1 – Apr 7 | Onboarding flow: sign-up → first grade in under 2 minutes | Not Started |
| Apr 1 – Apr 14 | Billing polish: all Stripe flows tested, usage limits visible | Not Started |
| Apr 7 – Apr 14 | Error handling pass: friendly messages everywhere, no stack traces | Not Started |
| Apr 14 | BETA LAUNCH — Invite first 20–50 testers | Gate |
|  | PHASE 3: BETA ITERATION |  |
| Apr 14 – May 15 | Collect and triage beta feedback (weekly check-ins) | Not Started |
| Apr 14 – May 15 | Fix top 10 issues from beta testers | Not Started |
| Apr 21 – May 8 | Analytics setup: funnels, sign-ups, grade completion rate | Not Started |
| May 1 – May 15 | Email system: welcome, grading results, sighting alerts (via Resend) | Not Started |
|  | PHASE 4: LAUNCH PREP |  |
| May 15 – Jun 7 | Load testing: 100 concurrent users, identify bottlenecks | Not Started |
| May 15 – Jun 14 | Landing page optimization: hero, social proof, SEO, /sdcc page | Not Started |
| Jun 1 – Jun 21 | Nice-to-haves sprint (SMS alerts, demo mode, collection gallery) | Not Started |
| Jun 14 – Jun 21 | Chrome Web Store submissions (2–3 week review period) | Not Started |
|  | PHASE 5: FINAL QA & SDCC |  |
| Jun 21 – Jul 7 | Full regression test pass (updated Session 59 test plan) | Not Started |
| Jul 1 – Jul 14 | SDCC booth prep: QR codes, demo devices, banner/signage | Not Started |
| Jul 7 – Jul 18 | Code freeze — bug fixes only, no new features | Not Started |
| Jul 18 – Jul 22 | Dress rehearsal: full demo run-through, backup plans | Not Started |
| Jul 23 | LAUNCH AT SDCC | D-Day |

# SDCC Booth Strategy

The booth is the product demo. Everything should drive people to scan a comic on their phone and see the result.

Booth Setup

- Large QR code banner: “Scan Your Comic — Free AI Grade in 60 Seconds”

- 2–3 demo tablets/phones for walk-up demos

- Sample comics to grade live (mix of grades: a 9.8, a 6.0, a 3.0)

- Monitor showing real-time grading results (demo loop or live feed)

SDCC Promo Offer

- SDCC-exclusive: sign up at the con and get 5 free grades (normally 2)

- Promo code: SDCC2026 — first month of Pro free

- Business cards / stickers with QR code for people who don’t sign up on the spot

Demo Script (60-Second Pitch)

“Have a comic you’re not sure about grading? Slab Worthy tells you the grade AND whether it’s worth the money to send in. Takes 60 seconds. Scan this QR code, snap 4 photos, and you’ll know if your book is slab-worthy.”

Backup Plan

WiFi at SDCC can be unreliable. Bring a mobile hotspot. If the server goes down, have a pre-recorded demo video on the monitor showing the full grading flow. Keep the team’s phones on cellular as backup demo devices.

# Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Grading consistency not reliable enough by April | Beta testers lose trust; can’t demo at booth | Start this first (Feb 24). If it’s not there by March 31, delay beta to May and simplify scope |
| Anthropic API costs spike with real users | Margins disappear or we hit rate limits | Monitor costs during beta. Set hard daily caps per user. Budget $500/mo for API during beta, $2K/mo at launch |
| SDCC booth WiFi is terrible | Live demos fail | Mobile hotspot, offline demo video, pre-graded sample results as fallback |
| Render free/starter tier can’t handle traffic | Site goes down during launch | Load test in May. Upgrade Render plan by June. Set up health monitoring with auto-alerts |
| Chrome Web Store review takes too long | Extensions not published by SDCC | Submit by June 14 (5+ weeks before). Have direct download (.crx) as backup |
| Beta testers find major UX issues | Scramble to fix before launch | That’s why we have beta. April–May is specifically for this. Triage ruthlessly: fix blockers, defer cosmetics |
| Scope creep eats the timeline | Must-haves aren’t done | This roadmap is the scope. If it’s not on the Must-Have list, it waits until after SDCC |

# Open Decisions

Items that need your input before we proceed:

| # | Decision | Options | Decide By |
| --- | --- | --- | --- |
| 1 | Free tier grade limit (currently undefined) | 2 / 3 / 5 grades | Mar 7 |
| 2 | Beta tester recruitment strategy | Friends / Reddit / LCS / All | Mar 21 |
| 3 | SDCC booth size and budget | Small table / Full booth | Apr 1 |
| 4 | Promo offer structure | Free grades / Discount / Both | May 15 |
| 5 | Analytics provider | Google Analytics / Plausible / PostHog | Mar 14 |
| 6 | Render plan tier for launch | Starter ($7) / Standard ($25) / Pro ($85) | Jun 1 |